## Sheet1
SavingsUnited - Single Theme Project
Move all sites to a single them running on webpack
Part 1: Consolidate
Milestone 1 |  |  | Milestone 2 |  | Milestone 3 |  | Milestone 4 | Milestone 5
flat_2017_webpacked |  |  | flat_2016_webpacked |  | remove rebatly_flat |  | WLS to flat_2016_webpacked | remove flat_2016
Goal: Get rid of flat_2017_mobile and only use the webpacked version. Therefore we have to update the existing webpacked version with all the changes we implemented into 2017_mobile in the past. Currently it is way behind. After we merged the changes the theme we can switch the currently running sites (kupon.pl) to 2017_webpacked and remove the 2017_mobile from the code |  |  | Goal: We want to migration our main theme to webpack. Therefore create a child-theme flat_2016_webpacked which relies on 2016_flat files. All assetc (js, CSS, images) and view files should fallback whenever possible. We create a child-theme because the migration from all sites to 2016_webpacked will take some time and we dont want to have havy maintainance work |  | Goal: Remove rebatly theme and migrate all rebatly sites to flat_2016_webpacked |  | Goal: Move all remaining WLS sites to flat_2016_webpacked and get rid of style settings. Also move all custom styles from "custom head scripts" into the dedicated theme overwrites.css files | Goal: remove flat_2016 and make flat_2016_webpacked the only full desktop theme left. Therefore we have to merge all files into 2016_webpacked and make it a full theme containing all assets and views.
Update 2017_webpacked with all changes of 2017_mobile
Switch all sites using 2017_mobile to 2017_webpacked or decide if we keep them all running on 2016
remove 2017_mobile rom code
Create child-theme for 2016_webpacked but only create files that have to be different and fallback to 2016 whenever possible
Rollout on SU branded sites
Rollout 2016_webpacked on rebatly sites one by one
remove rebatly_flat from code
Move WLS to flat_2016_webpacked one by one. Try to get rid of style settings and custom head scripts
make 2016_webpacked no childtheme anymore
remove flat_2016 from code
Part 2: Innovate (to be defined)
Milestone 1 |  |  | Milestone 2 |  | Milestone 3
design |  |  | development |  | rollout
Goal: After having all sites running on webpack we can continue with the creation of the single template. The curent situation is that we are planning to extend flat_2017_webpacked to all user agents and viewports. Currently we only serve mobile users with flat_2017_webpacked. We have to check the designs and see how we have to adopt them to be fully functional specially for WLS |  |  | Goal: Use the design drafts and evaluate if ist possible to build the new theme on top of flat_2017_webpacked. Develop all the features |  | Goal: Rollout new theme too all sites and remove all other themes from code. At this stage we should be having a single webpack based theme that serves all of our sites
evaluate needs specially for WLS. Also consider all findings we have from kupon.pl switch (are the features really an improvement)
review current design studies for that needs
draft definite define guide for development
evaluate if we have to create a new them or can extend flat_2017_webpacked
Develop the theme
Rollout to all sites
remove flat_2016_wepacked